## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Riya |  | Faced error in extracting the data json file for sentiment analysis | 2nd | Single developer | Logical | Used different way for analysing | 2025-01-23 | Closed
2 | Riya |  | Mail integration with webhook in zapier didn’t worked | 3rd | Single developer | Standards | Changed the action and trigger part for integration | 2025-01-24 | Closed
3 | Riya |  | Didn’t got expected result in response automation | 3rd | Single developer | Logical | Changed prompt | 2025-01-24 | Closed
4 | Riya |  | Faced errors while extracting the model from ipynb file, used pickle files for it, but wast able to connect them in app | 4th | Single developer | Standards | Just extracted main functions from ipynb files and saved as python file to call them directly in app | 2025-01-25 | Closed
5 | Riya |  | app was able to run but didn’t connected with the functions | 4th | Single developer | Logical | Tried calling the functions directly in app by giving required parameters | 2025-01-25 | Open

## Sheet2
Logical
User Interface
Maintainability
Standards
Others